## Safety Code
Cycling Ireland Event Safety Code
SAFETY CODE
• Cycling Ireland require that all events run under its regulations take place in an environment that is safe for participants, event personnel and general public. It is recognised that owing to the nature of events run under its regulations (e.g., road races, downhill races, non-competitive events etc.) it is extremely difficult to eliminate all risks. Safety is the responsibility of event organisers, event personnel and participants and everyone has a role to play in ensuring we adequately manage risks that cannot be eliminated.
• This Safety Code applies to events run under the auspices of a Cycling Ireland affiliated club, Commission, Provincial Executive or Sub-Committee
1. GENERAL GUIDELINES
• An Event Organiser must appoint a Safety Officer, the Event Organiser may also be the Safety Officer. The Safety Officer should be selected based on experience, competence, control, cooperation and communication.
• The Event Organiser is responsible for appointing a Safety Officer and for the implementation of this Safety Code. The Safety Officer should:
- Be present at planning meetings;
- Assist in the preparation of the Risk Assessment;
- Act in an advisory capacity on safety issues;
- Implement safety measures to reduce identified risks and be in attendance at event itself;
- Liaise as necessary with relevant authorities.
• In applying this Safety Code Event Organisers/Safety Officers must recognise that the degree of risk involved will vary depending
on factors such as the number of participants, experience of participants, nature of route, whether the event is of a competitive nature etc. For example there is a large difference between a mass-participation event of 4,000 (relatively) inexperienced cyclists and a club race of 30 experienced cyclists.
• Marshals are to be made aware of their role and responsibilities as outlined in the Cycling Ireland sign-on sheet (“.... function of the marshal is only to indicate direction”)
and any special requirements recognised in the Risk Assessment.
• A pre-event briefing, which may be verbal and/or written, must be provided to participants. The pre-event briefing should cover (as applicable)
- The requirement for participants to abide by the rules of the road;
- Responsibility of participants to be mindful of their own safety and the safety of others;
- An outline of the course and any particular hazards such as junctions, descents, poor surfaces, etc.;
- The distance, number of laps to be covered, prime locations etc.
• A Risk Assessment (see appendix 2 as an example) must be completed by the Safety Officer. The purpose of a Risk Assessment is
to identify hazards and measures that reduce the risk posed by hazards to an acceptable level.
2. Traffic/Course Safety
Traffic and course hazards probably pose the greatest risks
and Event Organisers must put in place steps to minimise the risk and inconvenience to traffic which may encounter the event and also to minimise the risk posed by the course itself. Steps to be considered include:
• Local authorities to be advised, as per local authority
requirements, in advance of road usage - provide route maps, dates, times, likely number of participants, number of separate events etc.;
• Garda/P.S.N.I. to be informed in line with required regulations (it is advised to notify Garda/P.S.N.I.) at least twelve weeks prior to the event;
• Lead vehicle(s) (sufficient to cover breaks that may form) with appropriate signage and lighting to warn oncoming traffic of the event, road user’s should be warned where there are sizeable groups;
• Consider appointment of motorbike marshals to aid the safe passage of participants;
• The course must be reconnoitred and marshals appointed at appropriate locations;
• Only those deemed competent by the Safety Officer are to be appointed as marshals;
• Each marshal point must be contactable by mobile phone/two-way radio;
• Marshals should be equipped with a hi-vis vest, whistle and flag;
• Warning signs placed as appropriate advising the general public an event is in progress;
• Warning signs placed as appropriate advising participants of particular hazards;
• Directional arrows to be provided warning of junctions;
• Advance warning to local residents through the use of signs, local newspapers, local radio;
• Particular consideration should be given to start/finish areas;
• A Risk Assessment for the course must be completed and any additional controls identified put in place - see example attached as appendix 2;
• For off-road events particular attention should be paid to reducing the risk posed by steep drops, wooden surfaces, tree-trunks, gate-posts, roots, stumps, rocks etc.;
• The Safety Officer should review the Risk Assessment and satisfy themselves that all safety measures are in place.
3. First Aid/Medical Cover
All open events (as per Cycling Ireland’s General Administrative and Technical Regulations - “A race open to holders of full
licences and/or restricted licences where appropriate and/or one day licences (excluding holders of club licences) which have been approved by the Cycling Ireland”) require, as a minimum, first aid personnel to be in attendance. The Safety Officer must assess the level of first aid required, steps to be considered include:
• Is an ambulance required or are trained First Aiders sufficient;
• Is it best for the ambulance/First Aiders to follow the participants or be placed at strategic locations?;
• Brief first aid personnel (a First Aider is a person over 18 years old who holds a first aid certificate) on route details, likely hazards, event duration;
• Ensure that first aid crew are easily contactable and test communications prior to the event start;
• For mass-participation events ensure that participants are issued a “helpline” number;
• Advise local hospitals of the event;
• participant numbers, nature of the event etc.;
• Ensure all marshals are aware of the first aid/emergency contact number;
• Ensure that contact numbers for local hospitals, ambulance support crews are to hand.
4. Participants and Event Personnel
• Participants must:
- Have a bicycle that is in good working order (which complies with relevant Technical Regulations);
- Wear a hard-shell helmet;
- Be mindful of the need to act in a manner that takes account of their own safety and the safety of others;
- Ensure their fitness level is appropriate given the nature of the event;
- Ensure their nutritional requirements can be met;
- Be conversant with and obey the rules of the road;
- Familiarise themselves with the event route;
- “Sign-on” for the event;
- Be aware that marshals are not empowered to stop traffic;
- For downhill, BMX events wear full personal protection equipment - full-face helmets are compulsory;
• Commissaires are responsible for the general sporting organisation of a race and not for safety, however a Commissaire may, if dissatisfied on any matter of safety, take action as they deem appropriate;
• Event personnel should:
- Be of a responsible age;
- Be appropriately briefed and clear as to their role;
- Wear any PPE (e.g., hi-vis vest) as identified in the Risk Assessment;
- Remain at their post until informed that they are no longer required;
- “Sign-on” for the event.

## Timetable
Appendix 1
Timetable for Event Organisers
Pre- Calendar Deadline
Apply to Cycling Ireland for a calendar date as per the instructions issued by Cycling Ireland.
Four Months Before
Go over the course and identify any changes since the completion (if any) of the previous Risk Assessment and complete a preliminary Risk Assessment; Identify and book race headquarters (ideally with changing and shower facilities), for off-road events confirm with landowner; Book first aid cover; Notify (and provide required information to) relevant local authorities and Garda/P.S.N.I.; Book other equipment as required - photo-finish, PA system, finish podium, barriers, race radios, catering, media coverage, signage, lead vehicles, neutral support, cars;
Preceding Week and On the Day
Finalise the Risk Assessment; Check that there have been no late hazards - road-works, sweep any identified loose debris if practicable, etc.; Have directional signs to the race HQ in place; Ensure that warning signs are in place; Cash float for sign-on desk, pins, stationery (sign-on sheets etc.); Place route markers on route; Display route details, information on particular hazards; Brief all personnel and participants; Submit results to Cycling Ireland; Pay expenses to Commissaires etc.; Note details of any incidents (time, place, contact details for those involved, nature of incident and any injuries suffered) and advise Cycling Ireland of details; Clean the start/finish areas, race route and race HQ; Check all participants for valid licences.
Aftermath
Send letters of thanks as appropriate to local authorities, Garda, sponsors, first aiders etc.; Note any improvements for future events; Remove any signs, barriers etc. erected for the event.

## Event Risk Assessment
Appendix 2
EVENT DETAILS RISK ASSESSMENT
Name of Event: | Fermanagh 200 Audax Event
Event Organiser and Contact Details: | Paul Burchmore, Ph.0044 7900 263960. 28 Agharainey Road, Kesh, Co Fermanagh, BT93 1SD. E-Mail: p.burchmore@btinternet.com
Event Safety and Contact Details: | Paul Burchmore, Ph.0044 7900 263960. 28 Agharainey Road, Kesh, Co Fermanagh, BT93 1SD. E-Mail: p.burchmore@btinternet.com
Event Date(s): | 13th May 2017
Type of Event (road race, leisure spin, downhill, etc.) | 200kms Audax/Leisure Event
Risk/Hazard | Existing measures to mitigate risk | Further mitigating actions required
TRAFFIC SAFETY CODE
Start area, Ballinmallard Football Club. Potential danger to Cyclists/Motorists | Instruct Riders to park in approved Car Park. Use off-road area for Sign-On and briefing prior to Start. | Recruit helpers to assist with sign-on to minimise delays.
Competitor Car Parking, risk to Cyclists, Pedestrians | Safe Parking available in Football Club at Start.
Sign-On, potential risk to Cyclists. | No risk to entrants, as using Football Club for sign-on.
Unexpected hazards (e.g. roadworks, adverse weather conditions etc.) | The route will be checked in the 2 weeks preceeding the event. Cyclists will be verbally informed of any road works at pre-start Riders Briefing. | For very poor road conditions or severe road works, consider possibility of route change/diversion to avoid area if possible.
Route related issues | Cyclists will be verbally informed at the event Briefing that the route will not be signed or marshalled, and that they must at all times obey the rules of the road. This information will also be posted on the event webpage on Audax Ireland website, and advised pre-event to all participants by e-mail. A detailed route-sheet will be given to all riders, and Sat Nav routes will be made available prior to the event for use of participants. | Self-reliance is a key part of riding Audax events. This requirement is made clear on the Audax Ireland website, in all pre-event informataion, and on the event entry form. This is a pre-entry event, there will be no entries accepted on the day.
Route Controls | There will be several Control points around the route, where riders must obtain proof of passage to confirm they have ridden the full course. These Controls are located in safe areas, off the road, such as Filling Stations with food facilities. Riders will be off the road, and will not present any danger to themselves or others. This is a self-supported event. Participants must carry or purchase their own refreshments. This will be made clear to participants before the event, and at Briefing.
Secret Control | There will be an unannounced Secret Control, to ensure riders complete the full course. The Control is in a safe area. This is a self-supported event. Participants must carry or purchase their own refreshments.
Finish area, Ballinamallard Football Club | The Finish is in Ballinamallard Football Club, with secure parking for Bikes and Cars. Due to the length of the event (200kms) and small numbers expected to take part, riders will be finishing in small groups or solo, and will not present any hazard to themselves or others.
FIRST AID/MEDICAL COVER
This is a Leisure Event, with a small number (< 20) of participants expected. Riders are not racing and will travel in small groups at their preferred pace. The aim of the event is to finish the distance within the overall time-limit, which is set at 15kph minimum average pace. | There is no First Aid cover provided. However several participants have First Aid training and all participants will assist any rider who is in difficulty to the best of their ability. | Self-reliance is a key part of riding Audax events. This requirement is made clear on the Audax Ireland website, in all pre-event informataion, and on the event entry form. This is a pre-entry event, there will be no entries accepted on the day.
Inability to communicate | Ensure all key Officials and Safety Officer are contactable. | Officials to carry Mobile Numbers for all riders, and riders will have Organisers contact number noted on their routsheets for use in emergencies.
PARTICIPANTS
Participants not following route | Detailed Routesheet provided to all participants. Sat Nav routes available for use if desired. Organisers contact details will be noted on the routesheet, for use if required.
Cycling at night | Riders will be instructed to wear High-Viz clothing after dark. Any rider who does not do so may be excluded from the event. Riders must carry front and back lights, and will be advised to carry spare lights also, in the event of any issue with their main lights.
Dehydration/exhaustion | This is a self-supported event. Participants must carry or purchase their own refreshments. This will be made clear to participants before the event, and at Briefing. | Self-reliance is a key part of riding Audax events. This requirement is made clear on the Audax Ireland website, in all pre-event informataion, and on the event entry form. This is a pre-entry event, there will be no entries accepted on the day. Riders will have Organisers contact number noted on their routesheets for use in emergencies.
Injuries resulting from crashes | Hazards minimised through route risk assessment. Compulsory wearing of helmets.
Mechanical breakdowns | There is no Mechanical Support. In the spirit of Audax events all participants will be made aware that they should be self-reliant and able to carry out basic repairs. Essential tools and spares should be carried. | Self-reliance is a key part of riding Audax events. This requirement is made clear on the Audax Ireland website, in all pre-event informataion, and on the event entry form. This is a pre-entry event, there will be no entries accepted on the day.
Participants not insured | Event to be sanctioned by Cycling Ireland and therefore fall under Cycling Ireland’s insurance scheme. All participants will be required to have a CI Licence, or to take out a 1-day Licence. All participants will be required to ‘sign-on’ at the Start.
OTHER HAZARDS
Slips, trips and falls | All areas to be kept free of clutter. There are adequate refuse bins at the Start, and at Controls. | Bicycles to be parked carefully, and with consideration for pedestrians and other cyclists.
Accidents, DNF's | Riders will have Organisers contact number noted on their routesheets for use in emergencies. All DNF's should report in to Organiser so they are accounted for. | The organiser will endeavour to collect any riders who are experiencing severe difficulties. However self-reliance is a key part of riding Audax events. This requirement is made clear on the Audax Ireland website, in all pre-event informataion, and on the event entry form. This is a pre-entry event, there will be no entries accepted on the day.

## Route Risk Assessment
Appendix 4
KMS | LOCATION | DIRECTION TO TAKE | HAZARD | RISK (H-high, M-medium, L-low) | STEPS TO REDUCE RISK TO LOW | RACE/ADDITIONAL NOTES | ETA (first passage) | ETA (last passage)
15.1 | Irvinestown | Right | Right Turn | M | 15.1km. Caution, Right Turn | Notes on Routesheet. No additional action required. | 08.30 | 9.00
56.3 | Belleek | Straight on | Cross Main Rd | M | 56.3km. Caution crossing main road. Note on Route-sheet to take extreme care before proceeding. | Notes on Routesheet. No additional action required. | 09.50 | 11.45
65 | after Garrison | Straight on | Long Climb | L | 65km. Start Long (16km) ascent. | Notes on Routesheet. No additional action required. | 10.06 | 12.20
81 | Knockmore Road | Straight on | Steep Descent | M | 81km. Steep descent for 3km. Advise Caution on routesheet. | Notes on Routesheet. No additional action required. | 10.45 | 13.24
99 | Mullylust Road Junction | Straight on | Steep Descent | M | 99km. Moderate/Steep descent for 4km. Advise Caution on routesheet. | Notes on Routesheet. No additional action required. | 11.20 | 14.35
104.9 | Belcoo | Right | Right Turn | M | 104.9km. Caution, Right Turn onto A4. Advise Caution on routesheet. | Notes on Routesheet. No additional action required. | 11.30 | 14.50
131.4 | Derrylin Rd Junction | Right | Right Turn | M | 131.4km. Caution, Right Turn onto Derrylin Road. Advise Caution on routesheet. | Notes on Routesheet. No additional action required. | 12.24 | 16.45
146.5 | Lisnaskea | Right | Right Turn | M | 146.5km. Caution, Right Turn onto Main St, Lisnaskea. Advise Caution on routesheet. | Notes on Routesheet. No additional action required. | 12.48 | 17.45
160.8 | Errasallagh | Straight on | Steep Descent | M | 160.8km. Moderate/Steep descent for 3km. Advise Caution on routesheet. | Notes on Routesheet. No additional action required. | 13.20 | 18.36
167.5 | Eshnasillogue More | Straight on | Steep Descent | M | 167.5km. Moderate/Steep descent with small climbs, for 6km. Advise Caution on routesheet. | Notes on Routesheet. No additional action required. | 13.30 | 18.45

## Safety Checklist
Appendix 5
Event Safety Checklist
Event: Fermanagh 200 Audax |  |  | Total Distance: 203.7 KM, LAPS OF: N/A
EVENT OFFICIALS | CHECK | COMMENTS |  | NAME | MOBILE PH | RADIO
Race Director |  | Event Organiser |  | Paul Burchmore | 0044 7900 263960 | N/A
Safety Officer |  | Not applicable to Audax Leisure Event |  | Paul Burchmore | 0044 7900 263960 | N/A
Chief Marshal |  | Not applicable to Audax Leisure Event
Commissaire 1 |  | Not applicable to Audax Leisure Event
Commissaire 2 |  | Not applicable to Audax Leisure Event
Commissaire 3 |  | Not applicable to Audax Leisure Event
EMERGENCY SERVICES | CHECK | COMMENTS |  | NAME | MOBILE PH | RADIO
Ambulance |  | Not applicable to Audax Leisure Event
First Aid |  | Not applicable to Audax Leisure Event
General |  | Not applicable to Audax Leisure Event
Doctor 1 On Call |  | Not applicable to Audax Leisure Event
Doctor 2 On Call |  | Not applicable to Audax Leisure Event
Hospital 1 On Call |  | Not applicable to Audax Leisure Event
Hospital 2 On Call |  | Not applicable to Audax Leisure Event
Fire Brigade (RTA) Local Garda/P.S.N.I. |  | Not applicable to Audax Leisure Event
OTHER MEASURES | CHECK | COMMENTS |  | NAME | MOBILE PH | RADIO
Circuit Traffic & Traffic Management |  | Not applicable to Audax Leisure Event
Stop/go system if required |  | Not applicable to Audax Leisure Event
Lead cars - signs on car, lights on etc |  | Not applicable to Audax Leisure Event
Course inspected |  | Yes, Course will be pre-ridden in the 2 weeks preceding the event. This will act as a check for the Route-sheet, and to gather information on Road-works or other hazards.
Course markings - directional and warnings |  | Not applicable to Audax Leisure Event
Start/Finish - barriers, crowd control etc |  | Not applicable to Audax Leisure Event
Gardai/P.S.N.I. in Attendance |  | Not applicable to Audax Leisure Event
Marshals (static and mobile) - hi-vis vests flags and whistles |  | Not applicable to Audax Leisure Event
Race communication - radios in place and tested, mobile numbers |  | Not applicable to Audax Leisure Event
Briefings given to participants and officials |  | There will be a pre-Start Briefing for all participants. They will be reminded to follow the Rules of the Road, and given detals of any Road-works, Diversions, Hazards etc.
Riders support - neutral service, broom wagon |  | None. This is an Audax event, and participants will be aware that they should be self-sufficient. This information will be advised to riders, posted on the Audax Ireland website, and included in the pre-event e-mail details. They should carry essential spares, and basic tools. The Organiser may be available to collect a small number of DNF's if necessary, but this cannot be guaranteed.

## Contact Details
Appendix 5
Event Personnel Contact Details
KM | Location | Instructions | ROLE: (Static marshal, Motorbike marshal, lead car driver etc.) | Marshal Name (S) | MOBILE #
|  |  | Event Organiser | Paul Burchmore | 0044 7900 263960